## Summary
Hello Add — project status
Generated (UTC) | 2026-04-13T02:12:10.739Z
Status | Count
Done | 9
Partial | 15
Pending | 0
How to read: Done = shipped in repo; Partial = needs env, QA, or polish; Pending = not started.

## Detailed status
Group | Task ID | Item | Status | Notes / location
Baseline | — | Campaigns: sort, bulk pause, CSV export, new campaign modal | Done | apps/dashboard/app/(dashboard)/campaigns/page.tsx
Baseline | — | Reports: Standard PDF + CEO briefing template + download API | Done | pdfGenerator, /api/reports/[id]/download
Baseline | — | Team: invites, accept flow, register with invite | Done | OrganizationInvite, /team, /accept-invite
Baseline | — | Auth: login, register, session cookie, /api/auth/me | Done | Cookie-based session
1 — Bug fixes | 1.1 | Report deduplication (same org/type/range within 5 min) | Done | apps/dashboard/app/api/reports/generate/route.ts
1 — Bug fixes | 1.2 | Invite email via Resend | Partial | sendInviteEmail wired; requires RESEND_API_KEY + verified domain in production
1 — Bug fixes | 1.3 | RBAC guards on write APIs | Partial | requireUserOrgRole / requireRole patterns in use; audit all routes vs spec
2 — Platform APIs | 2.1 | Meta Ads: real OAuth + Graph sync | Partial | OAuth/callback paths exist; completeness depends on META_APP_* env and testing
2 — Platform APIs | 2.2 | Google Ads: real OAuth + API | Partial | Connect/callback; live data requires GOOGLE_* credentials
2 — Platform APIs | 2.3 | LinkedIn: real OAuth + API | Partial | Connect/callback; live data requires LINKEDIN_* credentials
2 — Platform APIs | 2.4 | Sync engine + cron | Partial | Sync routes/cron flags in env; verify production scheduling
3 — AI + alerts | 3.1 | AI error detection / campaign analysis | Partial | Anthropic integration; tune per product goals
3 — AI + alerts | 3.2 | WhatsApp Business alerts | Partial | Integration + org settings; Cloud API tokens per org
3 — AI + alerts | 3.3 | Email alerts via Resend | Partial | Alert/report email paths; Resend config in env
4 — Reports polish | 4.1 | Branded PDF (Hello Add theme) | Partial | CEO + standard templates; further white-label optional
4 — Reports polish | 4.2 | Real Excel (.xlsx) export | Partial | exceljs in project; confirm all export entry points use xlsx where spec requires
5 — Mobile | 5.1 | Dashboard mobile responsive layout | Partial | Ongoing; test key pages on small viewports
6 — Onboarding + billing | 6.1 | Onboarding wizard + OAuth next=/onboarding | Done | Settings org; trial fields
6 — Onboarding + billing | 6.2 | Razorpay subscriptions + billing UI | Partial | API routes + billing tab; production needs live Razorpay keys + webhooks
7 — Agency | 7.1 | Agency multi-client: DB, APIs, overview table, client detail tabs | Partial | AgencyClientRelation, PATCH, AM/CM, History/Team/Notes; Leads tab still light
7 — Agency | 7.1 | Profile: editable contact & brand (PATCH) | Done | integrations page auth modals separate item below
7 — Agency | 7.2 | White-label client portal + signed links + branding settings | Partial | /client/[orgId]/*, token cookie; logo URL in settings — file upload optional follow-up
UX | — | Integrations: confirm sign-in modal before OAuth redirect | Done | apps/dashboard/app/(dashboard)/integrations/page.tsx
UX | — | Client portal signing: CLIENT_PORTAL_SECRET / NEXTAUTH_SECRET | Done | token.ts dev fallback + env docs